## Week1
PROJECT REPORT
Group | <Group 3>
Week | <05/09/2022-10/09/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | In Progress | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | In Progress | Overall contents as listed in the part I of the SRS document.
3 | Screen layouts of the system functions | In Progress | Listed in the part II located in SRS documents.
4 | Web Skeleton | In Progress | HTML, CSS, JS files.
5 | Design Document | In Progress | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | TanDM, KhaVKD | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | MinhNVA, TaiNHT | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | MinhNVA, TanDM | List all the functions of the website.
4 | Web Skeleton | MinhNVA, TaiNHT, TanDM, KhaVKD | Coding HTML, CSS, JS for website.
5 | Design Document | ThienNH | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | MinhNVA | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Create Diagram in SRS document | In Progress | Lack of experience in drawing Diagrams located in SRS documents.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Design template of web | 2023-05-19 | Requirements, layout, function.
2 | Weekly Report | 2023-05-19 | Fill in all the sections in the Excel Weekly Report file.
3 | SRS Template | 2023-05-19 | Overall contents as listed in the part I of the SRS document.
4 | Web Skeleton | 2023-05-19 | HTML, CSS, JS files.
5 | Design Document | 2023-05-19 | Overall contents as listed in the part I of the Design Document.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C24: ====== ID#AAAAfoGOFE8 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week2
PROJECT REPORT
Group | <Group 3>
Week | <08/05/2023-19/05/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | Completed | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | Completed | Overall contents as listed in the part I of the SRS document.
3 | Screen layouts of the system functions | Completed | Listed in the part II located in SRS documents.
4 | Web Skeleton | Completed | HTML, CSS, JS files.
5 | Design Document | Completed | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | TanDM, KhaVKD | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | MinhNVA, TaiNHT | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | MinhNVA, TanDM | List all the functions of the website.
4 | Web Skeleton | MinhNVA, TaiNHT, TanDM, KhaVKD | Coding HTML, CSS, JS for website.
5 | Design Document | ThienNH | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | MinhNVA | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Create Diagram in SRS document | Completed | Lack of experience in drawing Diagrams located in SRS documents.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Design Database | 2023-05-26 | Design ERD, collect data.
2 | Coding Funtions | 2023-05-26 | Coding functions of web.
3 | Weekly Report | 2023-05-26 | Fill in all the sections in the Excel Weekly Report file.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE4 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week3
PROJECT REPORT
Group | <Group 3>
Week | <26/05/2023-02/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | Completed | List functions, features, complexity, planned code iteration, divide task for members.
2 | Coding Funtions | In Progress | Coding functions of web.
3 | Design Database | In Progress | Design ERD, collect data.
4 | Web Skeleton | Completed | HTML, CSS, JS files.
5 | Design Document | Completed | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | TanDM, KhaVKD | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | MinhNVA, TaiNHT | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | MinhNVA, TanDM | List all the functions of the website.
4 | Web Skeleton | MinhNVA, TaiNHT, TanDM, KhaVKD | Coding HTML, CSS, JS for website.
5 | Design Document | ThienNH | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | MinhNVA | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Create Diagram in SRS document | Completed | Lack of experience in drawing Diagrams located in SRS documents.
2 | Design Database | In Progress | Lack of experience in designing DB
3 | Coding Funtions | In Progress | Lack of experience in ReactJS
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Design Database | 2023-06-02 | Design ERD, collect data.
2 | Coding Funtions | 2023-06-02 | Coding functions of web.
3 | Weekly Report | 2023-06-02 | Fill in all the sections in the Excel Weekly Report file.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE4 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week4
PROJECT REPORT
Group | <Group 3>
Week | <02/06/2023-09/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | Completed | List functions, features, complexity, planned code iteration, divide task for members.
2 | Coding Funtions in Iteration 1 | Completed | Coding functions of web.
3 | Design Database | Completed | Design ERD, collect data.
4 | Web Skeleton | Completed | HTML, CSS, JS files.
5 | Design Document | Completed | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | TanDM, KhaVKD | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | MinhNVA, TaiNHT | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | MinhNVA, TanDM | List all the functions of the website.
4 | Web Skeleton | MinhNVA, TaiNHT, TanDM, KhaVKD | Coding HTML, CSS, JS for website.
5 | Design Document | ThienNH | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | MinhNVA | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Create Diagram in SRS document | Completed | Lack of experience in drawing Diagrams located in SRS documents.
2 | Design Database | Completed | Lack of experience in designing DB
3 | Coding Funtions | Completed | Lack of experience in ReactJS
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Edit BackLog template for Iteration 2 | 2023-06-09 | List functions, features, complexity, planned code iteration, divide task for members.
2 | Coding Funtions in Iteration 2 | 2023-06-09 | Coding functions of web.
3 | Weekly Report | 2023-06-09 | Fill in all the sections in the Excel Weekly Report file.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE4 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week5
PROJECT REPORT
Group | <Group 3>
Week | <09/06/2023-16/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Edit BackLog template for Iteration 2 | Completed | List functions, features, complexity, planned code iteration, divide task for members.
2 | Coding Funtions in Iteration 2 | In Progress | Coding functions of web.
3 | Fix bug for Iteration 1 | In Progress | Fixing functions in the web.
4 | Web Skeleton | Completed | HTML, CSS, JS files.
5 | Design Document | Completed | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | TanDM, KhaVKD | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | MinhNVA, TaiNHT | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | MinhNVA, TanDM | List all the functions of the website.
4 | Web Skeleton | MinhNVA, TaiNHT, TanDM, KhaVKD | Coding HTML, CSS, JS for website.
5 | Design Document | ThienNH | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | MinhNVA | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Coding Funtions in Iteration 2 | In Progress | Lack of experience in ReactJS
2 | Fix bug for Iteration 1 | In Progress | Lack of experience in ReactJS
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Coding Funtions in Iteration 2 | 2023-06-16 | List functions, features, complexity, planned code iteration, divide task for members.
2 | Fix bug for Iteration 1 | 2023-06-16 | Coding functions of web.
3 | Weekly Report | 2023-06-16 | Fill in all the sections in the Excel Weekly Report file.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE4 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week6
PROJECT REPORT
Group | <Group 3>
Week | <16/06/2023-23/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Edit BackLog template for Iteration 2 | Completed | List functions, features, complexity, planned code iteration, divide task for members.
2 | Coding Funtions in Iteration 2 | Completed | Coding functions of web.
3 | Fix bug for Iteration 1 | Completed | Fixing functions in the web.
4 | Web Skeleton | Completed | HTML, CSS, JS files.
5 | Design Document | Completed | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | TanDM, KhaVKD | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | MinhNVA, TaiNHT | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | MinhNVA, TanDM | List all the functions of the website.
4 | Web Skeleton | MinhNVA, TaiNHT, TanDM, KhaVKD | Coding HTML, CSS, JS for website.
5 | Design Document | ThienNH | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | MinhNVA | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Coding Funtions in Iteration 2 | Completed | Lack of experience in ReactJS
2 | Fix bug for Iteration 1 | Completed | Lack of experience in ReactJS
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Coding Funtions in Iteration 3 | 2023-06-23 | List functions, features, complexity, planned code iteration, divide task for members.
2 | Fix bug for Iteration 2 | 2023-06-23 | Coding functions of web.
3 | Weekly Report | 2023-06-23 | Fill in all the sections in the Excel Weekly Report file.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE4 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week7
PROJECT REPORT
Group | <Group 3>
Week | <23/06/2023-30/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Edit BackLog template for Iteration 3 | Completed | List functions, features, complexity, planned code iteration, divide task for members.
2 | Coding Funtions in Iteration 3 | In Progress | Coding functions of web.
3 | Fix bug for Iteration 2 | In Progress | Fixing functions in the web.
4 | Web Skeleton | Completed | HTML, CSS, JS files.
5 | Design Document | Completed | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | TanDM, KhaVKD | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | MinhNVA, TaiNHT | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | MinhNVA, TanDM | List all the functions of the website.
4 | Web Skeleton | MinhNVA, TaiNHT, TanDM, KhaVKD | Coding HTML, CSS, JS for website.
5 | Design Document | ThienNH | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | MinhNVA | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Coding Funtions in Iteration 3 | In Progress | Lack of experience in ReactJS
2 | Fix bug for Iteration 2 | In Progress | Lack of experience in ReactJS
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Coding Funtions in Iteration 3 | 2023-06-30 | List functions, features, complexity, planned code iteration, divide task for members.
2 | Fix bug for Iteration 2 | 2023-06-30 | Coding functions of web.
3 | Weekly Report | 2023-06-30 | Fill in all the sections in the Excel Weekly Report file.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE4 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week8
PROJECT REPORT
Group | <Group 3>
Week | <08/05/2023-19/05/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Edit BackLog template for Iteration 3 | Completed | List functions, features, complexity, planned code iteration, divide task for members.
2 | Coding Funtions in Iteration 3 | Completed | Coding functions of web.
3 | Fix bug for Iteration 2 | Completed | Fixing functions in the web.
4 | Web Skeleton | Completed | HTML, CSS, JS files.
5 | Design Document | Completed | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | TanDM, KhaVKD | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | MinhNVA, TaiNHT | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | MinhNVA, TanDM | List all the functions of the website.
4 | Web Skeleton | MinhNVA, TaiNHT, TanDM, KhaVKD | Coding HTML, CSS, JS for website.
5 | Design Document | ThienNH | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | MinhNVA | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Coding Funtions in Iteration 3 | In Progress | Lack of experience in ReactJS
2 | Fix bug for Iteration 2 | In Progress | Lack of experience in ReactJS
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Coding Funtions in Iteration 3 | 2023-07-07 | List functions, features, complexity, planned code iteration, divide task for members.
2 | Fix bug for Iteration 2 | 2023-07-07 | Coding functions of web.
3 | Weekly Report | 2023-07-07 | Fill in all the sections in the Excel Weekly Report file.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE4 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue